## Sheet1
Last Update: | En 1004.03 - NH Standard Process Track Interconnection Queue Report
2026-10-01
Project Number | Process Track | Nameplate Rating (kW) | Facility Export Capacity (kW) | Fuel Type | ESS Nameplate Rating (kW) | ESS Energy Rating (kWH) | ESS Coupling | Town/City | Substation Name | Circuit | Current Status | Date Application Deemed Complete | Date Impact Study Agreement Executed | Date Impact Study Completed | Date IA Sent | Date IA Signed | Date PTO Granted | Group Study Name | ASO Group Identifier
ERI-07245 | Standard | 2625 | 2625 | Solar | N/A | N/A | N/A | Boscawen | Boscawen | C13W3 | Perform Mods | 2023-04-11 | 2023-06-12 | 2023-11-27 | 2024-09-20 | 2024-10-07
ERI-07337 | Standard | 4980 | 4980 | Solar | N/A | N/A | N/A | Concord | West Portsmouth | C15W2 | Witness Test | 2023-04-27 | 2023-07-03 | 2023-10-23 | 2024-01-19 | 2024-02-16
ERI-09258 | Standard | 4999 | 4999 | Solar | N/A | N/A | N/A | Concord | Terrill Park | C16X4 | Perform Mods | 2023-10-25 | 2023-12-26 | 2024-04-17 | 2024-06-06 | 2024-08-06
ERI-09603 | Standard | 4000 | 4000 | Solar | N/A | N/A | N/A | Boscawen | Boscawen | C13W3 | On Hold | 2023-11-27 | 2024-02-05 | 2024-09-05
ERI-09998 | Standard | 4990 | 4990 | Solar | N/A | N/A | N/A | Penacook | Penacook | C4X1 | On Hold | 2024-03-15 | 2024-05-10 | 2025-02-05
ERI-10184 | Standard | 1760 | 1760 | Solar | N/A | N/A | N/A | Bow | Iron Works Road | C22W3 | Perform Mods | 2024-05-14 | 2024-07-25 | 2024-11-07 | 2025-05-06 | 2025-05-19
ERI-10186 | Standard | 2816 | 2816 | Solar | N/A | N/A | N/A | Bow | Bow Junction | C7W3 | Waiting for Mods Fee | 2024-05-17 | 2024-07-25 | 2024-10-29 | 2025-11-04 | 2025-11-10
ERI-10207 | Standard | 4999 | 4999 | Solar | N/A | N/A | N/A | Loudon | Hollis | C8X3 | Perform Mods | 2024-05-21 | 2024-07-11 | 2024-10-24 | 2025-01-10 | 2025-02-10
ERI-10446 | Standard | 480 | 480 | Solar | N/A | N/A | N/A | Bow | Bow Bog | C18W2 | Perform Mods | 2024-07-17 | 2024-07-26 | 2025-07-11 | 2025-07-14 | 2025-08-04
ERI-10652 | Standard | 5000 | 5000 | Solar | N/A | N/A | N/A | Canterbury | Boscawen | C13W1 | On Hold | 2025-06-24
ERI-11770 | Standard | 6625 | 1000 | Natural Gas | N/A | N/A | N/A | Hampton | Guinea Switching | E18X1 | Impact Study | 2025-09-30 | 2026-04-16
ERI-11882 | Standard | 3300 | 3300 | Solar | N/A | N/A | N/A | Plaistow | Timberlane | E13X3 | Waiting for ISA Signature | 2025-11-11 | 2026-02-09 | 2026-06-26 | 2026-08-05
ERI-11898 | Standard | 4950 | 4950 | Solar | N/A | N/A | N/A | Hampton | Winnacunnet Road | E46X1 | Waiting for ISA Signature | 2025-11-20 | 2026-02-12 | 2026-07-17 | 2026-09-17
ERI-12064 | Standard | 724.5 | 724.5 | Solar | N/A | N/A | N/A | Seabrook | Cemetery Lane | E15X1 | Create ISA | 2026-01-22 | 2026-04-15 | 2026-08-03